## EffortEstimate
| Topic | Nosotros | Cliente | Diego | Do Hyun | Andrés | Andrew | Emiliano | Total |  |  | Costo por actividad
Project Management | Project Management | O | S | 8 | 10 | 10 | 5 | 3 | 36 | 10.2564 | % PM del Total | -44904.5
Project Definition | Scoping | O | C | 4 | 4 | 13 | 4 | 6 | 31 | 19.6581 | % PD del Total | -38092.25
| Requirements and design | O | C | 17 | 1 | 10 | 5 | 5 | 38 | PM debe ser el 10% del proyecto |  | -46807.5
Architecture | VPC architecture | O | S |  |  |  |  | 5 | 5 | PD debe ser el 20% del proyecto |  | -6670
| Server setup | S | O |  |  |  |  | 6 | 6 |  |  | -8004
| Notification and chatting system | O | O |  | 2 |  |  | 4 | 6 |  |  | -8056
| User authentication integration | O | S |  | 3 |  |  | 4 | 7 |  |  | -9416
| NLP pipeline | O | S |  |  | 10 | 5 |  | 15 |  |  | -17102.5
Database | E-R diagram design | O | C |  |  | 2 |  |  | 2 |  |  | -2346.5
| Schema definition | O | S |  |  | 5 |  |  | 5 |  |  | -5866.25
Backend | Payment API | O | S | 10 | 10 |  |  |  | 20 |  |  | -26350
| Database connection | O | S |  | 5 | 5 |  |  | 10 |  |  | -12666.25
| Connection with document validation libraries | O | C |  | 5 | 5 | 5 |  | 15 |  |  | -18036.25
| Cloud instance creation | O | C | 1 | 4 |  | 3 |  | 8 |  |  | -9937
| Connection with agencies | O | C |  |  |  |  | 4 | 4 |  |  | -5336
Frontend | UI/UX design | O | S |  | 6 |  |  |  | 6 |  |  | -8160
| Framework implementation | O | S |  | 5 |  |  | 6 | 11 |  |  | -14804
| Responsive design | O | S |  | 4 |  |  | 6 | 10 |  |  | -13444
| Statistics per access level | O | S |  |  |  |  | 5 | 5 |  |  | -6670
| Natural language search | O | S |  | 2 | 5 |  |  | 7 |  |  | -8586.25
| Guiding questions search | O | S |  | 2 |  |  |  | 2 |  |  | -2720
| Financing plan search | O | S |  | 2 |  |  |  | 2 |  |  | -2720
| Component creation | O | S |  | 5 |  |  |  | 5 |  |  | -6800
Security Integration | User data encryption | O | S |  |  |  | 5 | 5 | 10 |  |  | -12040
| Document decomposition | O | S |  |  |  |  | 10 | 10 |  |  | -13340
Validation | Unit testing | O | S | 10 |  |  |  |  | 10 |  |  | -12750
| Component testing | O | S |  |  |  | 10 |  | 10 |  |  | -10740
| Architecture testing | O | S |  |  | 5 |  |  | 5 |  |  | -5866.25
| User acceptance testing | C | O |  |  |  | 10 |  | 10 |  |  | -10740
| System Integration Testing (SIT) | O | C |  | 1 |  | 5 |  | 6 |  |  | -6730
| Pentesting | O | S | 10 |  |  |  |  | 10 |  |  | -12750
| Automatic document validation | O | S |  |  |  | 10 |  | 10 | La ruta critica es el maximo de MD por cada actividad |  | -10740
| Route testing | O | S |  |  |  | 4 |  | 4 | % Ejecución del Total |  | -4296
| Type validation | O | S | 10 |  |  |  |  | 10 | 68.661 |  | -12750
|  |  | Total | 70 | 71 | 70 | 71 | 69 | 351 |  |  | -436237.5
S = support, C = collaborator, O = owner
20 Man Day per month
Days in the project: 75 (15 weeks, 5-day work weeks)
Max Total MD: 375

## MarginAnalysis
Project Margin analysis
% del trabajo
Esfuerzo total en MD | 351 | 100%
Diego | 70 | 19.94%
Do Hyun | 71 | 20.23%
Andrew | 71 | 20.23%
Emiliano | 69 | 19.66%
Andrés | 70 | 19.94%
Target CPI | 1
Costo Operacional Diego | -1275 | Colegiatura + Gasolina
Costo Operacional Do Hyun | -1360 | Colegiatura + Comidas + Gasolina + Desgaste Mental + Desgaste Físico
Costo Operacional Andrew | -1074 | Colegiatura + Gasolina
Costo Operacional Emiliano | -1334 | Colegiatura + Transporte + Comida
Costo Operacional Andrés | -1173.25 | Colegiatura + Transporte
Revenue ($) | 875000
Total internal cost ($) | -436237.5
Total profit ($) | 438762.5
Margin (%) | 50.14% | Un margen debe quedar alrededor de 50%