## EffortEstimate
| Topic | Nosotros | Cliente | Diego | Do Hyun | Andrés | Andrew | Emiliano | Total |  |  | Costo por actividad
Project Management | Project Management | O | S | 8 | 10 | 10 | 5 | 3 | 36 | 10.2857 | % PM del Total | -44568.4524
Project Definition | Scoping | O | C | 4 | 4 | 13 | 4 | 6 | 31 | 19.7143 | % PD del Total | -38118.1548
| Requirements and design | O | C | 17 | 1 | 10 | 5 | 5 | 38 | PM debe ser el 10% del proyecto |  | -46974.0873
Architecture | VPC architecture | O | S |  |  |  |  | 5 | 5 | PD debe ser el 20% del proyecto |  | -6801.5873
| Server setup | S | O |  |  |  |  | 6 | 6 |  |  | -8161.9048
| Notification and chatting system | O | S |  | 2 |  |  | 4 | 6 |  |  | -8061.2698
| User authentication integration | O | S |  | 3 |  |  | 4 | 7 |  |  | -9371.2698
| NLP pipeline | O | S |  |  | 10 | 5 |  | 15 |  |  | -17187.5
Database | E-R diagram design | O | C |  |  | 2 |  |  | 2 |  |  | -2346.5
| Schema definition | O | S |  |  | 5 |  |  | 5 |  |  | -5866.25
Backend | Payment API | O | S | 10 | 10 |  |  |  | 20 |  |  | -25850
| Database connection | O | S |  | 5 | 5 |  |  | 10 |  |  | -12416.25
| Connection with document validation libraries | O | C |  | 5 | 5 | 5 |  | 15 |  |  | -17871.25
| Cloud instance creation | O | C | 1 | 4 |  | 3 |  | 8 |  |  | -9788
| Connection with agencies | O | C |  |  |  |  | 4 | 4 |  |  | -5441.2698
Frontend | UI/UX design | O | S |  | 6 |  |  |  | 6 |  |  | -7860
| Framework implementation | O | S |  | 4 |  | 5 | 6 | 15 |  |  | -18856.9048
| Responsive design | O | S |  | 4 |  |  | 6 | 10 |  |  | -13401.9048
| Statistics per access level | O | S |  |  |  |  | 5 | 5 |  |  | -6801.5873
| Natural language search | O | S |  | 2 | 5 |  |  | 7 |  |  | -8486.25
| Guiding questions search | O | S |  | 2 |  |  |  | 2 |  |  | -2620
| Financing plan search | O | S |  | 2 |  |  |  | 2 |  |  | -2620
| Component creation | O | S |  | 5 |  |  |  | 5 |  |  | -6550
Security Integration | User data encryption | O | S |  |  |  | 5 | 5 | 10 |  |  | -12256.5873
| Document decomposition | O | S |  |  |  |  | 10 | 10 |  |  | -13603.1746
Validation | Unit testing | O | S | 10 |  |  |  |  | 10 |  |  | -12750
| Component testing | O | S |  |  |  | 10 |  | 10 |  |  | -10910
| Architecture testing | O | S |  |  | 5 |  |  | 5 |  |  | -5866.25
| User acceptance testing | C | O |  |  |  | 5 |  | 5 |  |  | -5455
| System Integration Testing (SIT) | O | C |  | 1 |  | 5 |  | 6 |  |  | -6765
| Pentesting | O | S | 10 |  |  |  |  | 10 |  |  | -12750
| Automatic document validation | O | S |  |  |  | 10 |  | 10 |  |  | -10910
| Route testing | O | S |  |  |  | 4 |  | 4 | % Ejecución del Total |  | -4364
| Type validation | O | S | 10 |  |  |  |  | 10 | 68.5714 |  | -12750
|  |  | Total | 70 | 70 | 70 | 71 | 69 | 350 | 21.3675 |  | -434400.4048
S = support, C = collaborator, O = owner
20 Man Day per month
Days in the project: 75 (15 weeks, 5-day work weeks)
Max Total MD: 375

## MarginAnalysis
Project Margin analysis
% del trabajo
Esfuerzo total en MD | 350 | 100%
Diego | 70 | 20%
Do Hyun | 70 | 20%
Andrew | 71 | 20.29%
Emiliano | 69 | 19.71%
Andrés | 70 | 20%
Target CPI | 1
Costo Operacional Diego | -1275 | Colegiatura + Gasolina
Costo Operacional Do Hyun | -1310 | Colegiatura + Comidas + Gasolina + Desgaste Mental + Desgaste Físico
Costo Operacional Andrew | -1091 | Colegiatura + Gasolina
Costo Operacional Emiliano | -1360.3175 | Colegiatura + Transporte + Comida
Costo Operacional Andrés | -1173.25 | Colegiatura + Transporte
Revenue ($) | 875000
Total internal cost ($) | -434400.4048
Total profit ($) | 440599.5952
Margin (%) | 50.35% | Un margen debe quedar alrededor de 50%

## Costos (hidden)
Costos fijos | Cantidad | Costo por mes
Droplets | 4
DNS | 1
Load Balancer | 1
VPC | 1
RDB | 1
Non RDB | 1
Bucket | 2