## EffortEstimate
| Topic | Nosotros | Cliente | Diego | Do Hyun | Andrés | Andrew | Emiliano | Total |  |  | Costo por actividad
Project Management | Project Management | C | O | 8 | 10 | 10 | 5 | 3 | 36 | 10.2273 | % PM del Total | -44904.5
Project Definition | Scoping | O | C | 4 |  | 13 |  | 4 | 21 | 16.7614 | % PD del Total | -25688.25
| Requirements and design | O | C | 17 | 1 | 10 | 5 | 5 | 38 | PM debe ser el 10% del proyecto |  | -46807.5
Validation | Unit testing | O | S | 10 |  |  |  |  | 10 | PD debe ser el 20% del proyecto |  | -12750
| Component testing | O | S |  |  |  | 10 |  | 10 |  |  | -10740
| Architecture testing | O | S |  |  | 5 |  |  | 5 |  |  | -5866.25
| User acceptance testing | S | O |  |  |  | 10 |  | 10 |  |  | -10740
| System Integration Testing (SIT) | S | O |  | 1 |  | 5 |  | 6 |  |  | -6730
| Pentesting | O | S | 10 |  |  |  |  | 10 |  |  | -12750
| Drop validation | C | O |  |  |  | 5 |  | 5 | Con esto sale la ruta crítica y de ahí hacemos el gantt |  | -5370
| Automatic document validation | O | S |  |  |  | 10 |  | 10 | La ruta critica es el maximo de MD por cada actividad |  | -10740
| Type validation | O | S | 10 |  |  |  |  | 10 |  |  | -12750
Backend | Payment API | O | S | 10 | 10 |  |  | 5 | 25 |  |  | -33020
| Database connection | O | S |  | 5 | 5 |  |  | 10 |  |  | -12666.25
| Connection with document validation libraries | O | C |  | 5 | 5 | 5 | 4 | 19 |  |  | -23372.25
| Connection with agencies | O | C |  |  |  |  | 4 | 4 |  |  | -5336
Frontend | UI/UX design | O | S |  | 7 |  |  | 4 | 11 |  |  | -14856
| Framework implementation | O | S |  | 5 |  |  | 6 | 11 |  |  | -14804
| Responsive design | O | S |  | 4 |  |  | 6 | 10 |  |  | -13444
| Statistics per access level | O | S |  |  |  |  | 5 | 5 |  |  | -6670
| Natural language search | O | S |  | 2 | 5 |  |  | 7 |  |  | -8586.25
| Guiding questions search | O | S |  | 2 |  |  |  | 2 |  |  | -2720
| Financing plan search | O | S |  | 2 |  |  |  | 2 |  |  | -2720
| Component creation | O | S |  | 5 |  |  |  | 5 |  |  | -6800
Database | E-R diagram design | O | C |  |  | 2 |  |  | 2 |  |  | -2346.5
| Schema definition | O | S |  |  | 5 |  |  | 5 |  |  | -5866.25
Architecture | Server setup | C | O |  | 5 |  |  | 6 | 11 |  |  | -14804
| Notification system | O | S |  | 2 |  |  | 4 | 6 |  |  | -8056
| User authentication integration | O | S |  | 3 |  |  | 4 | 7 |  |  | -9416
| NLP pipeline | O | S |  | 3 | 10 | 10 |  | 23 |  |  | -26552.5
Security Integration | User data encryption | O | S |  |  |  | 5 | 4 | 9 | % Ejecución del Total |  | -10706
| Document decomposition | O | S |  |  |  |  | 7 | 7 | 73.0114 |  | -9338
|  |  | Total | 69 | 72 | 70 | 70 | 71 | 352 |  |  | -437916.5
S = support, C = collaborator, O = owner
20 Man Day per month
Days in the project: 75 (15 weeks, 5-day work weeks)
Max Total MD: 375

## MarginAnalysis
Project Margin analysis
% del trabajo
Esfuerzo total en MD | 352 | 100%
Diego | 69 | 19.6%
Do Hyun | 72 | 20.45%
Andrew | 70 | 19.89%
Emiliano | 71 | 20.17%
Andrés | 70 | 19.89%
Target CPI | 1
Costo Operacional Diego | -1275 | Colegiatura + Gasolina
Costo Operacional Do Hyun | -1360 | Colegiatura + Comidas + Gasolina + Desgaste Mental + Desgaste Físico
Costo Operacional Andrew | -1074 | Colegiatura + Gasolina
Costo Operacional Emiliano | -1334 | Colegiatura + Transporte + Comida
Costo Operacional Andrés | -1173.25 | Colegiatura + Transporte
Revenue ($) | 875833
Total internal cost ($) | -437916.5
Total profit ($) | 437916.5
Margin (%) | 50% | Un margen debe quedar alrededor de 50%
Account 10 years margin analysis
Revenue
Item | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
License | 1440000 | [9 empty] | 1440000
Maintenance |  |  |  | 288000 | 288000 | 288000 | 288000 | 288000 | 288000 | 288000 | 2016000
Rentals |  |  |  | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 120000 | 840000
Implementation Payments by Client | 500000 | 1000000 | 500000 | [7 empty] | 2000000
Sub-Total | 1940000 | 1000000 | 500000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 6296000
After Royalties | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
License | 648000 | [9 empty] | 648000
Maintenance |  |  |  | 163008 | 163008 | 163008 | 163008 | 163008 | 163008 | 163008 | 1141056
Rentals |  |  |  | 60360 | 60360 | 60360 | 60360 | 60360 | 60360 | 60360 | 422520
Implementation Payments by Client | 500000 | 1000000 | 500000 | [7 empty] | 2000000
Sub-Total | 1148000 | 1000000 | 500000 | 223368 | 223368 | 223368 | 223368 | 223368 | 223368 | 223368 | 4211576
Cost (Open Source route)
Implemenation | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Apache Solr
Sub-Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost (Half premium route)
Implemenation | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Sub-Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost (Full premium route)
Implemenation | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
AWS Dynamo DB
AWS Amazon Comprehend
AWS Amazon Rekognition
AWS App Runner
Sub-Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Flow per Year (before Royalties)
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Total | 1940000 | 1000000 | 500000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 408000 | 6296000
Rate | 5%
NPV | 5225949.98
IRR | #NUM!
MNA Cash Flow per Year (after Royalties)
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Total
Total | 1148000 | 1000000 | 500000 | 223368 | 223368 | 223368 | 223368 | 223368 | 223368 | 223368 | 4211576
Rate | 5%
NPV | 3548783.633
IRR | #NUM!